## README
InfraLens — 2-Week Delivery Plan (Excel)
Generated for CEO / eng tracking. PDF skipped per request.
Priority: P0 Critical ¦ P1 High ¦ P2 Medium ¦ P3 Low
Roles: Super Admin → Org Admin → DevOps Lead → DevOps Engineer → Developer → Viewer
Onboarding: Existing GitHub repo OR Create new repo; GitHub/Azure via OAuth or tokens/secrets
E2E: Documents → Architecture → Terraform → Infra apply → App code
Total estimated hours (all tasks): 147
Update Status column on Task_Backlog as work proceeds (Not started / In progress / Done / Blocked).
Sheets
README — this cover
Task_Backlog — all tasks with priority, day, hours, owner, deps
Timeline — day-by-day focus
Priority_Summary — hours by priority
RBAC_Matrix — who can do what
Onboarding_Flow — wizard steps
Gaps_Status — YES/NO vs 2-week target
Test_Plan — QA cases
Hours_by_Epic — effort rollup
RACI — accountability

## Task_Backlog
ID | Epic | Task | Priority | Week | Day | Est_Hours | Owner_Role | Depends_On | Status | Acceptance_Criteria | Notes
T01 | RBAC | Add role field to User + seed Super Admin | P0-Critical | 1 | D1 | 4 | Backend | - | Not started | JWT includes role; admin seeded | Foundation
T02 | RBAC | Role hierarchy helpers + require_role middleware | P0-Critical | 1 | D1 | 4 | Backend | T01 | Not started | Viewer gets 403 on write APIs
T03 | RBAC | Users & Roles management page (Settings) | P0-Critical | 1 | D1 | 6 | Frontend | T01 | Not started | Org Admin+ can assign roles
T04 | RBAC | Map Risk Engine gates to minimum roles | P1-High | 1 | D1 | 3 | Backend | T02 | Not started | two_person needs DevOps Lead+
T05 | Onboarding | Onboarding wizard shell + first-login redirect | P0-Critical | 1 | D2 | 5 | Frontend | T01 | Not started | Zero projects forces wizard | Replaces bare ProjectModal
T06 | Onboarding | Path A: Existing project — list GitHub repos + select | P0-Critical | 1 | D2 | 6 | Full-stack | T05,T08 | Not started | Project created with mapped repo
T07 | Onboarding | Path B: New project — create GitHub repo by name | P0-Critical | 1 | D2 | 6 | Full-stack | T05,T08 | Not started | Repo created on user account + linked
T08 | Onboarding | GitHub connect: PAT/token method in wizard | P0-Critical | 1 | D2 | 4 | Backend | T05 | Not started | Identity shown after connect | Reuse connections store
T09 | Onboarding | Azure connect step in wizard (SP secrets) | P0-Critical | 1 | D2 | 4 | Full-stack | T05 | Not started | Subscription identity validated
T10 | Onboarding | GitHub OAuth start/callback (env-configured) | P1-High | 1 | D3 | 6 | Backend | T08 | Not started | OAuth and PAT both work | Needs GITHUB_OAUTH_* env
T11 | Onboarding | Azure dual-auth UI (OAuth/device if feasible + secrets) | P1-High | 1 | D3 | 5 | Full-stack | T09 | Not started | User can choose either method | Secrets path must ship
T12 | Onboarding | Align Settings page with same dual-auth UX | P2-Medium | 1 | D3 | 3 | Frontend | T10,T11 | Not started | Wizard and Settings consistent
T13 | Platform | Action diff fields + hard rollback gate on write | P0-Critical | 1 | D4 | 5 | Backend | - | Not started | Empty rollback rejects create_action
T14 | Platform | Informed approval UI (dashboard + chat) | P0-Critical | 1 | D4 | 5 | Frontend | T13 | Not started | Shows risk, dry-run, rollback, rationale
T15 | Platform | Engineering Memory write + list_precedent API | P1-High | 1 | D4 | 5 | Backend | - | Not started | Last N similar decisions on approval
T16 | Platform | Break-glass sessions (Lead+) + audit | P1-High | 1 | D4 | 5 | Backend | T02,T15 | Not started | TTL expire; memory entry mandatory
T17 | Release | Week-1 harden, regression, ACR deploy | P0-Critical | 1 | D5 | 6 | DevOps | T01-T16 | Not started | Healthy Container App revision
T18 | E2E Delivery | delivery_runs model + stage machine API | P0-Critical | 2 | D6 | 6 | Backend | T06 | Not started | Stages persist per project | docs→arch→TF→infra→code
T19 | E2E Delivery | Ingest documents + architecture proposal stage | P0-Critical | 2 | D6 | 6 | Full-stack | T18 | Not started | Architecture accepted by Lead+
T20 | E2E Delivery | Generate Terraform as PR / file bundle | P0-Critical | 2 | D7 | 8 | Full-stack | T19,T07 | Not started | Never silent apply; plan as ActionDiff
T21 | E2E Delivery | Gated terraform/infra apply + code scaffold PR | P1-High | 2 | D7 | 6 | Full-stack | T20,T13 | Not started | Prod apply needs Lead+
T22 | E2E Delivery | Delivery checklist UI in chat/plan mode | P1-High | 2 | D7 | 5 | Frontend | T18 | Not started | User sees stage progress
T23 | Modules | Pipeline + Security: propose fix/patch PR | P1-High | 2 | D8 | 6 | Backend | T13,T02 | Not started | Developer+ propose; Lead merge/prod
T24 | Modules | IaC gated apply + FinOps gated resize proposals | P1-High | 2 | D8 | 6 | Backend | T13 | Not started | Deletes stay two_person
T25 | Modules | Release confidence promote + Incident runbook tiers | P1-High | 2 | D8 | 6 | Backend | T13,T04 | Not started | Diagnose auto; invasive gated
T26 | QA | Full integration/E2E test day + checklist | P0-Critical | 2 | D9 | 8 | QA/Full-stack | T17-T25 | Not started | Both onboarding paths + RBAC matrix pass
T27 | Docs | Generate Excel task plan (this file) + refresh status | P1-High | 2 | D10 | 2 | PM | - | In progress | Priority/time/owner columns complete | PDF skipped per request
T28 | Release | Final deploy + CEO demo (onboarding + E2E) | P0-Critical | 2 | D10 | 6 | DevOps | T26 | Not started | Demo script ready

## Timeline
Week | Day | Date_Window | Focus | Key_Deliverables | Hours_Budget | Exit_Criteria
1 | D1 | Week1 Day1 | RBAC | Roles, JWT, Users page | 17 | Role enforcement works
1 | D2 | Week1 Day2 | Onboarding core | Existing vs New project; GitHub PAT; Azure secrets | 25 | Both project paths create workspace
1 | D3 | Week1 Day3 | OAuth dual-auth | GitHub OAuth + Azure dual UI; Settings aligned | 14 | OAuth or token both usable
1 | D4 | Week1 Day4 | Platform safety | Rollback gate, informed approvals, memory, break-glass | 20 | Cannot propose without rollback
1 | D5 | Week1 Day5 | Deploy checkpoint | Regression + ACR + demo | 6 | Healthy revision
2 | D6 | Week2 Day6 | E2E start | delivery_runs + docs/arch stages | 12 | Stage machine works
2 | D7 | Week2 Day7 | E2E TF/infra/code | TF PR, gated apply, checklist UI | 19 | TF proposal path works
2 | D8 | Week2 Day8 | Six modules | Thin actuators RBAC-aware | 18 | Propose-PR / gated paths smoke
2 | D9 | Week2 Day9 | Testing | E2E + RBAC + onboarding matrix | 8 | Checklist signed
2 | D10 | Week2 Day10 | Ship + demo | Final deploy + Excel refresh + CEO demo | 8 | Demo complete

## Priority_Summary
Priority | Meaning | Task_Count | Total_Est_Hours | Must_Ship_By
P0-Critical | Blocks demo / security / onboarding | 16 | 89 | End of assigned day
P1-High | Needed for full MVP story | 11 | 55 | End of week
P2-Medium | Polish / consistency | 1 | 3 | If time remains
P3-Low | Nice-to-have / later phase | 0 | 0 | After 2 weeks

## RBAC_Matrix
Capability | Super_Admin | Org_Admin | DevOps_Lead | DevOps_Engineer | Developer | Viewer
Manage users/roles | Y | Y | N | N | N | N
Create project / onboarding | Y | Y | Y | Y | Y | N
Connect GitHub/Azure secrets | Y | Y | Y | Y | Y | N
Create GitHub repo | Y | Y | Y | Y | Y | N
Chat read / dashboard view | Y | Y | Y | Y | Y | Y
Propose write actions / PRs | Y | Y | Y | Y | Y | N
Approve human_approval | Y | Y | Y | Y | N | N
Approve two_person / prod apply | Y | Y | Y | N | N | N
Break-glass | Y | Y | Y | N | N | N
Delete project | Y | Y | N | N | N | N
Start E2E delivery | Y | Y | Y | Y | Y | N
Accept architecture / apply staging | Y | Y | Y | Y | N | N

## Onboarding_Flow
Step | Path | User_Action | System_Action | Auth_Option | Priority | Est_Hours
0 | Both | Login / first visit | If no projects → open wizard | - | P0-Critical | 2
1 | Both | Choose Existing or New project | Branch wizard | - | P0-Critical | 2
2 | Both | Connect GitHub | Store encrypted token/OAuth | OAuth OR PAT | P0-Critical | 6
3 | Existing | Select repo from list | Create project + map repos | GitHub session | P0-Critical | 4
3 | New | Enter repo name + visibility | Create repo on GitHub account | GitHub write scope | P0-Critical | 5
4 | Both | Connect Azure (optional now) | Validate + store connection | OAuth/device OR SP secrets | P0-Critical | 5
5 | Both | Finish | Land Dashboard/Chat; optional Start Delivery | - | P0-Critical | 2

## Gaps_Status
Requirement | Current | Target_2wk | Priority | Linked_Tasks
Gate by action class x blast radius | YES | YES | P0-Critical | -
Safety-direction never gated | YES | YES | P0-Critical | -
Six agent modules scaffold | YES | YES | P0-Critical | -
Time-boxed approvals | YES | YES | P0-Critical | -
Full action diff + rollback required | NO | MVP | P0-Critical | T13,T14
Informed approvals UI | NO | MVP | P0-Critical | T14
Break-glass | NO | MVP | P1-High | T16
Engineering Memory retrieval | NO | MVP | P1-High | T15
RBAC 6 roles + manage page | NO | MVP | P0-Critical | T01-T04
Onboarding existing vs new repo | NO | MVP | P0-Critical | T05-T12
GitHub/Azure OAuth + token options | PARTIAL (tokens only) | MVP | P0-Critical | T08-T11
E2E docs→arch→TF→infra→code | NO | MVP | P0-Critical | T18-T22
Module actuators | PARTIAL (diagnose) | MVP thin | P1-High | T23-T25

## Test_Plan
Test_ID | Area | Case | Priority | Type | Day | Pass_Criteria
QA01 | RBAC | Viewer 403 on write | P0-Critical | API | D1 | 403 returned
QA02 | RBAC | Lead can break-glass; Engineer cannot | P1-High | API | D4 | 403 for Engineer
QA03 | Onboarding | Existing repo path creates project | P0-Critical | E2E | D2/D9 | Project + repo mapped
QA04 | Onboarding | New repo path creates GitHub repo | P0-Critical | E2E | D2/D9 | Repo exists + linked
QA05 | Onboarding | PAT and OAuth both connect GitHub | P1-High | Integration | D3 | Identity shown
QA06 | Platform | Write without rollback rejected | P0-Critical | Unit/API | D4 | 400/ValueError
QA07 | Platform | Approval shows dry-run + rollback | P0-Critical | UI | D4 | Fields visible
QA08 | E2E | Docs→arch→TF PR happy path | P0-Critical | E2E | D9 | PR opened
QA09 | Modules | Propose patch PR smoke | P1-High | Integration | D8 | Action queued/approved
QA10 | Regression | Chat stream + branding + login | P0-Critical | Regression | D5/D9 | No ContextVar/eqip bugs

## Hours_by_Epic
Epic | Tasks | Est_Hours | Priority_Mix | Week
Onboarding | 8 | 39 | P0-Critical:5, P1-High:2, P2-Medium:1 | 1
E2E Delivery | 5 | 31 | P0-Critical:3, P1-High:2 | 2
Platform | 4 | 20 | P0-Critical:2, P1-High:2 | 1
Modules | 3 | 18 | P1-High:3 | 2
RBAC | 4 | 17 | P0-Critical:3, P1-High:1 | 1
Release | 2 | 12 | P0-Critical:2 | 1,2
QA | 1 | 8 | P0-Critical:1 | 2
Docs | 1 | 2 | P1-High:1 | 2
TOTAL | 28 | 147

## RACI
Workstream | Super_Admin | Org_Admin | DevOps_Lead | DevOps_Engineer | Developer | Viewer
Define roles / users | A/R | C | C | I | I | I
Onboarding wizard | A | C | C | R | R | I
GitHub/Azure connections | A | C | C | R | R | I
Risk gates / approvals | A | C | R | R | C | I
E2E delivery apply prod | A | C | R | C | I | I
Module propose PRs | A | I | C | R | R | I
Break-glass | A | R | R | I | I | I
CEO demo / docs Excel | A | C | C | R | I | I