# InfraLens — 2-Week Delivery Plan

Product: InfraLens (DevSecOps Skills Suite)

Audience: CEO / Engineering

Companion Excel: docs/InfraLens_2Week_Delivery_Plan.xlsx

Note: PDF was skipped. This Word file is the narrative document.

# 1. Purpose

This plan closes the gaps in the DevOps Intelligence Layer vision: safer approvals, RBAC, new-user onboarding (existing GitHub repo vs create new repo), end-to-end delivery (documents → architecture → Terraform → infra → code), and thin actuators for the six agent modules — within 2 weeks at MVP depth, with testing.

# 2. What we already have

Risk Engine gates by action class × blast radius (not by tool)

Safety-direction actions (rollback/mitigation) are never gated

Six agent modules as workflow scaffolds (diagnose/read-only skills)

Time-boxed finding approvals (nothing auto-executes on timeout)

Chat + Azure/GitHub connections via manual tokens in Settings

# 3. What we will build (2-week MVP)

RBAC: Super Admin → Org Admin → DevOps Lead → DevOps Engineer → Developer → Viewer + Users/Roles page

Onboarding wizard: Existing project (select GitHub repo) OR New project (create GitHub repo)

GitHub & Azure connect: OAuth/automatic AND manual token/secret options

Full action diff + hard rule: no rollback plan → cannot propose write

Informed approval UI (risk, dry-run, rollback, rationale)

Break-glass (DevOps Lead+) + Engineering Memory precedent

E2E delivery flow: docs → architecture → Terraform → gated apply → app code/PRs

Thin actuators for Pipeline, Release, IaC, Incident, Security/Patch, FinOps

# 4. Onboarding flow

New users (or any new project) get a wizard — not only a project name.

## Option A — Existing project

Connect GitHub (OAuth or Personal Access Token)

Select repository from the account/org list

Create InfraLens project linked to that repo

Connect Azure (OAuth/device flow or Service Principal secrets)

Finish → Dashboard / Chat

## Option B — New project

Connect GitHub

Enter desired repository name (and visibility)

App creates the repo on the user account

Create InfraLens project linked to the new repo

Connect Azure (same dual options)

Optional: start E2E delivery flow next

# 5. RBAC (initial roles)

| Role | Main powers (MVP) |
| --- | --- |
| Super Admin | Everything; users/roles; break-glass; system settings |
| Org Admin | Org users/roles; all org projects; break-glass |
| DevOps Lead | Prod / two-person approve; break-glass; workflows; write |
| DevOps Engineer | Propose write; approve normal human gates; run workflows |
| Developer | Chat, plan, propose PRs; onboard/create project; no prod apply |
| Viewer | Read-only dashboard/chat/wiki |

# 6. End-to-end delivery flow

After onboarding, the guided path is:

Understand documents / requirements

Propose infrastructure architecture (human accept for apply path)

Generate Terraform (as PR / bundle — never silent apply)

terraform plan as ActionDiff; apply gated by environment × role

Scaffold / update application code via PRs

Run intelligence modules; outcomes → Engineering Memory

# 7. Two-week timeline (summary)

## Week 1 — Platform + RBAC + Onboarding

D1: RBAC + Users page

D2: Onboarding wizard (existing vs new repo; PAT + Azure secrets)

D3: GitHub OAuth + dual-auth UX for GitHub/Azure

D4: Action diff/rollback gate, informed approvals, memory, break-glass

D5: Harden, deploy, demo checkpoint

## Week 2 — E2E + modules + ship

D6–D7: E2E delivery stages (docs → TF → infra → code)

D8: Six module thin actuators (RBAC-aware)

D9: Full testing day

D10: Final deploy + CEO demo; refresh Excel status

# 8. Effort snapshot

See Excel sheet Task_Backlog and Hours_by_Epic for full breakdown.

Approx. total estimated effort: ~147 hours across 28 tracked tasks (team parallelization assumed for a 2-week calendar).

# 9. Out of scope (later phase)

Full enterprise SSO / SCIM

Real canary traffic shifting

Automated flake retry + git bisect

True two-person with two distinct human identities (MVP uses Lead+ role + confirmations)

# 10. Related files

Excel (tasks, priority, time, RBAC, tests): docs/InfraLens_2Week_Delivery_Plan.xlsx

This Word document: docs/InfraLens_2Week_Delivery_Plan.docx